## Executive Summary
Grant Portfolio — Executive Summary
Illustrative portfolio for demonstration purposes ¦ Clean Air Fund India — sample analyst tracker
Portfolio comprises 5 active grants worth ₹1.72 crore. Overall utilisation is 47%. 1 grant(s) are high risk due to implementation or reporting delays. 3 report(s) are due or overdue within the current cycle.
Key Figures
Portfolio Value | 17200000
Total Disbursed | 8090000
Overall Utilisation | 47.03%
Active Grants | 4
High-Risk Grants | 1
Reports Due <30 Days | 3

## Dashboard
Portfolio Dashboard
Clean Air Fund India — Illustrative Grant Portfolio
PORTFOLIO VALUE |  |  | TOTAL DISBURSED | UTILISATION | ACTIVE GRANTS | HIGH-RISK GRANTS
17200000 |  |  | 8090000 | 47.03% | 4 | 1
Chart Data (auto-calculated — do not delete)
Grant | Total Budget | Disbursed | Utilisation %
Air Quality Monitoring | 4500000 | 3200000 | 71.11%
City Emissions Programme | 6800000 | 2100000 | 30.88%
CEO Clean Air Initiative | 1800000 | 1800000 | 100%
Clean Air & Health Project | 2900000 | 950000 | 32.76%
Community Awareness Campaign | 1200000 | 40000 | 3.333%
Status | Count
On Track | 2
Needs Attention | 1
Completed | 1
Delayed | 1
Risk | Count
Low | 3
Medium | 1
High | 1
Grant Health Score
Grant | Score | Rating
Air Quality Monitoring | 100 | 🟢 Green
City Emissions Programme | 75 | 🟡 Amber
CEO Clean Air Initiative | 100 | 🟢 Green
Clean Air & Health Project | 100 | 🟢 Green
Community Awareness Campaign | 30 | 🔴 Red
Reporting Calendar
Grant | Reporting Due | Status
Air Quality Monitoring | 2026-08-08 | 🟢 31 days remaining
City Emissions Programme | 2026-07-17 | 🟡 Due in 9 days
CEO Clean Air Initiative | 2026-07-10 | ✅ Final report submitted
Clean Air & Health Project | 2026-09-05 | 🟢 59 days remaining
Community Awareness Campaign | 2026-07-02 | 🔴 Overdue by 6 days

## Grant Tracker
Grant Tracker — Clean Air Fund India Portfolio (Illustrative)
Note: All figures are illustrative and for demonstration purposes only, based on publicly available information about CAF's India portfolio areas.
Grant Name | Partner | Focus | Total Budget (INR) | Disbursed (INR) | Remaining (INR) | % Utilised | Budget Remaining % | Start Date | End Date | Days Remaining | Progress % | Planned Disbursement | Variance % | Status | Risk | Reporting Due | Reporting Status | Health Score | Health Rating | Action Required
Air Quality Monitoring | Research Institute | Data and Modelling | 4500000 | 3200000 | 1300000 | 71.11% | 28.89% | 2025-04-01 | 2027-03-31 | 266 | 63.51% | 2858024.691 | 11.97% | On Track | Low | 2026-08-08 | 🟢 31 days remaining | 100 | 🟢 Green | None — on schedule, monitor next milestone
City Emissions Programme | State Pollution Control Board | Regulatory Implementation | 6800000 | 2100000 | 4700000 | 30.88% | 69.12% | 2025-06-01 | 2026-11-30 | 145 | 73.49% | 4997440.585 | -57.98% | Needs Attention | Medium | 2026-07-17 | 🟡 Due in 9 days | 75 | 🟡 Amber | Follow up with partner on procurement delays; request revised disbursement timeline
CEO Clean Air Initiative | Civil Society Organisation | Stakeholder Engagement | 1800000 | 1800000 | 0 | 100% | 0% | 2025-01-01 | 2026-06-30 | -8 | 100% | 1800000 | 0% | Completed | Low | 2026-07-10 | ✅ Final report submitted | 100 | 🟢 Green | Close out grant file; archive final report
Clean Air & Health Project | Public Health Foundation | Health Impact | 2900000 | 950000 | 1950000 | 32.76% | 67.24% | 2025-09-01 | 2027-02-28 | 235 | 56.88% | 1649541.284 | -42.41% | On Track | Low | 2026-09-05 | 🟢 59 days remaining | 100 | 🟢 Green | None — early implementation phase, on pace
Community Awareness Campaign | Urban Local Body | Citizen Engagement | 1200000 | 40000 | 1160000 | 3.333% | 96.67% | 2025-10-01 | 2026-09-30 | 84 | 76.92% | 923076.9231 | -95.67% | Delayed | High | 2026-07-02 | 🔴 Overdue by 6 days | 30 | 🔴 Red | Urgent check-in call; missed milestone, request cause and revised plan
Total / Portfolio |  |  | 17200000 | 8090000 | 9110000 | 47.03% | 52.97%
Formulas:
Days Remaining = [End Date]-TODAY()
Progress % = MIN(1,MAX(0,(TODAY()-[Start Date])/([End Date]-[Start Date])))
Reporting Status = IF([Status]="Completed","✅ Final report submitted",IF(([Reporting Due]-TODAY())<0,"🔴 Overdue by "&ABS([Reporting Due]-TODAY())&" days",IF(([Reporting Due]-TODAY())<=10,"🟡 Due in "&([Reporting Due]-TODAY())&" days","🟢 "&([Reporting Due]-TODAY())&" days remaining")))
Health Score = 100-IF([Status]="Delayed",20,IF([Status]="Needs Attention",10,0))-IF([Risk]="Medium",15,IF([Risk]="High",30,0))-IF(AND([Status]<>"Completed",([Reporting Due]-TODAY())<0),20,0)

## Finance & Deliverables
Finance & Deliverables Tracker
Note: Illustrative payment and deliverable records, linked to Grant Tracker figures.
Grant Name | Payment Request Submitted | Payment Approved | Invoice Received | Invoice Pending | Payment Date | Actual Payment (INR) | Expected Payment (INR) | Payment Variance (INR) | Deliverables Planned | Deliverables Completed | Completion % | Milestones Achieved | Next Milestone
Air Quality Monitoring | 2026-06-01 | 2026-06-10 | Yes | No | 2026-06-18 | 3200000 | 3200000 | 0 | 6 | 4 | 66.67% | Sensor network live in 3 cities | Mid-term data validation report
City Emissions Programme | 2026-06-15 |  | Yes | Yes |  | 2100000 | 2100000 | 0 | 5 | 2 | 40% | Baseline emissions inventory | Draft state implementation roadmap
CEO Clean Air Initiative | 2026-06-05 | 2026-06-12 | Yes | No | 2026-06-20 | 1800000 | 1800000 | 0 | 4 | 4 | 100% | All CEO roundtables completed | Final report submitted
Clean Air & Health Project | 2026-06-20 | 2026-06-28 | Yes | No | 2026-07-02 | 950000 | 950000 | 0 | 5 | 2 | 40% | Health impact baseline survey | Household exposure pilot results
Community Awareness Campaign | 2026-05-20 |  | No | Yes |  | 40000 | 40000 | 0 | 4 | 1 | 25% | Campaign launch event | Revised outreach plan (overdue)